## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TASCore TAS.01.00.1545_20181219_103623
February 15, 2019
Version 4.0

## Revision History
Revision History
Date | Version | Description | Author
11/14/2018 | 1 | Initial | Donald Fowlds/ Lisa Bruno
12/21/2018 | 2 | Final | Donald Fowlds/ Lisa Bruno
1/24/2019 | 3 | B6/B7 | Donald Fowlds/ Lisa Bruno
2/15/2019 | 4 | Adding B6 Regression | Donald Fowlds

## Test Execution Log
Test Case ID | User Story | Sprint | Build Executed | Date Executed | Tested By | Test Results (P/F) | Defect ID (Failed Tests)
TC3621: Verify order of the eProducts are now displayed in alphabetical order | US5027 | S3 | TAS.01.00.1490_20181009_144754 | 10/10/2018 07:24 AM EDT | Lisa Bruno | P
TC3621: Verify order of the eProducts are now displayed in alphabetical order | US5027 | SS | TAS.01.00.1517_20181108_103103 | 11/08/2018 10:33 AM EST | Lisa Bruno | P
TC3621: Verify order of the eProducts are now displayed in alphabetical order | US5027 | Pre -Prod | TAS.01.00.1545_20181219_103623 | 12/19/2018 01:03 PM EST | Donald Fowlds | P
TC3621: Verify order of the eProducts are now displayed in alphabetical order | US5027 | SS | TAS.01.00.1545_20181219_103623 | 01/23/2019 11:10 AM EST | Donald Fowlds | P
TC3626: Verify order of the eProducts are now displayed in alphabetical order | US5027 | S3 | TAS.01.00.1490_20181009_144754 | 10/10/2018 07:24 AM EDT | Lisa Bruno | P
TC3626: Verify order of the eProducts are now displayed in alphabetical order | US5027 | SS | TAS.01.00.1517_20181108_103103 | 11/08/2018 10:33 AM EDT | Lisa Bruno | P
TC3626: Verify order of the eProducts are now displayed in alphabetical order | US5027 | Pre -Prod | TAS.01.00.1545_20181219_103623 | 12/19/2018 10:59 AM EST | Donald Fowlds | P
TC3626: Verify order of the eProducts are now displayed in alphabetical order | US5027 | SS | TAS.01.00.1545_20181219_103623 | 01/23/2019 12:07 PM EST | Donald Fowlds | P
TC3732: Verify the Change Order of Product Lines in the Navigation Bar of TAS Portal | US5027 | S3 | TAS.01.00.1490_20181009_144754 | 10/19/2018 10:17 AM EDT | Kimberly Battles | P
TC3732: Verify the Change Order of Product Lines in the Navigation Bar of TAS Portal | US5027 | SS | TAS.01.00.1517_20181108_103103 | 11/08/2018 10:59 AM EDT | Kimberly Battles | P
TC3732: Verify the Change Order of Product Lines in the Navigation Bar of TAS Portal | US5027 | Pre -Prod | TAS.01.00.1545_20181219_103623 | 12/20/2018 09:58 AM EDT | Kimberly Battles | P
TC3732: Verify the Change Order of Product Lines in the Navigation Bar of TAS Portal | US5027 | SS | TAS.01.00.1545_20181219_103623 | 01/24/2019 10:00 AM EDT | Kimberly Battles | P
TC1174: Ensure alternative text for images is spelled and spaced correctly | US2202 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:37 PM EST | Donald Fowlds | P
TC1180: Navigate through web page with only a keyboard | US2216 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:09 PM EST | Donald Fowlds | P
TC1180: Navigate through web page with only a keyboard | US2216 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:55 AM EST | Donald Fowlds | P
TC1181: Ensure alternative text for images has proper punctuation and spacing | US2202 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:37 PM EST | Donald Fowlds | P
TC1182: Ensure field-sets are labelled appropriately | US2202 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:40 PM EST | Donald Fowlds | P
TC1183: Provide visual labels or instructions for user input | US2202 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:18 PM EST | Donald Fowlds | P
TC1186: Verify a 'Skip to main content' link is available and functional | US2219 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:09 PM EST | Donald Fowlds | P
TC1186: Verify a 'Skip to main content' link is available and functional | US2219 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:55 AM EST | Donald Fowlds | P
TC1187: Verify a timer is available to user when about to navigate away from site | US2220 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:09 PM EST | Donald Fowlds | P
TC1187: Verify a timer is available to user when about to navigate away from site | US2220 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:56 AM EST | Donald Fowlds | P
TC1241: Verify Modal Overlays Remain On-Screen After Active Focus is Removed From Navigational Items. | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:10 PM EST | Donald Fowlds | P
TC1241: Verify Modal Overlays Remain On-Screen After Active Focus is Removed From Navigational Items. | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:57 AM EST | Donald Fowlds | P
TC1244: Verify Website Notification Explaining user is About to leave TAS Domain is Keyboard Accessible. | US2227 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:11 PM EST | Donald Fowlds | P
TC1246: Verify that ""Leaving TAS Warning"" Countdown Timer can not be Manipulated by Multiple Clicks. | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:58 AM EST | Donald Fowlds | P
TC1433: Verify, for the ""ePharmacy"" navigational menu item button, the value inside each ARIA attribute is spelled correctly and corresponds to a valid value. | US3009 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:39 PM EST | Donald Fowlds | P
TC1455: Verify that the ""Here's how you know"" button displays discernable text for Screen Reader interaction. | US2205 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:44 PM EST | Donald Fowlds | P
TC1457: Verify that the ""ePharmacy"" navigational menu item button displays discernable text for Screen Reader interaction. | US2205 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:45 PM EST | Donald Fowlds | P
TC1468: MCCF EDI TAS Portal Index Page must have a way to bypass repeated blocks of content. | US2219 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:19 PM EST | Donald Fowlds | P
TC1478: The HTML document's favicon must have alternate text. | US2205 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:39 PM EST | Donald Fowlds | P
TC1479: The HTML document's ""eBusiness Solutions"" logo must have alternate text. | US2205 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:16 PM EST | Donald Fowlds | P
TC1480: The ""Site-wide Search"" form input element must have a unique label. | US2218 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:21 PM EST | Donald Fowlds | P
TC1481: The ""Contact Search"" form input element must have a label. | US2218 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:37 PM EST | Donald Fowlds | P
TC1492: Verify Tab Order | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:41 PM EST | Donald Fowlds | P
TC1493: Verify ""Skip to main content' element can be operated via keyboard | US2219 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:43 PM EST | Donald Fowlds | P
TC1494: Verify all primary navigation links can be operated via keyboard | US2216 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:34 PM EST | Donald Fowlds | P
TC1495: Verify all secondary navigation links can be operated via keyboard | US2216 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:34 PM EST | Donald Fowlds | P
TC1496: Verify Page loads in a specified amount of time | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:04 PM EST | Donald Fowlds | P
TC1520: Ensure summary and caption text(s) are different from each other. | US2211 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:33 PM EST | Donald Fowlds | P
TC1521: All cells in a <table> element that use the headers attribute must only refer to other cells of that same table | US2211 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:46 PM EST | Donald Fowlds | P
TC1522: All <th> elements and elements with role=columnheader/rowheader must have data cells they describe. | US2211 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:24 PM EST | Donald Fowlds | P
TC1524: For all text used in hyperlinks, buttons, and links, none of it can be repeated in the image alternative. | US3009 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:45 PM EST | Donald Fowlds | P
TC1525: Validate that the ""Skip to main content"" hyperlink displays discernable text for Screen Reader interaction. | US2205 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:11 PM EST | Donald Fowlds | P
TC1526: Validate that the ""eBusiness Solutions"" logo text hyperlink displays discernable text for Screen Reader interaction. | US2205 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:22 PM EST | Donald Fowlds | P
TC1533: Validate that the ""eBusinessSolutions@va.gov"" @mailto: hyperlink displays discernable text for Screen Reader interaction. | US2205 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:42 PM EST | Donald Fowlds | P
TC1534: <ul> and <ol> must only directly contain <li> content elements. | US3009 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:11 PM EST | Donald Fowlds | P
TC1535: Every <li> element in the page must be contained in a <ul> or a <ol> element. | US3009 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:36 PM EST | Donald Fowlds | P
TC1536: Check that the eRevenue Resources Link renders the user access to the eRevenue Sharepoint site. | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:03 PM EST | Donald Fowlds | P
TC1563: Selecting the ""Here's how you know"" hyperlink expands an accordion with additional user information. | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:03 PM EST | Donald Fowlds | P
TC1574: Ensure layout is designed so that it has a consistent look and feel across all web pages. | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:51 AM EST | Donald Fowlds | P
TC1575: Ensure only the content section of the page is being updated while navigating MCCF EDI TAS Portal. | US1406 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:51 AM EST | Donald Fowlds | P
TC1583: Verify a screen reader allows user to hear audio of secondary navigation bar | US2221 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:07 PM EST | Donald Fowlds | P
TC1583: Verify a screen reader allows user to hear audio of secondary navigation bar | US2221 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:53 AM EST | Donald Fowlds | P
TC1584: Verify a screen reader allows the user to hear the banner element | US2221 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:07 PM EST | Donald Fowlds | P
TC1584: Verify a screen reader allows the user to hear the banner element | US2221 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:53 AM EST | Donald Fowlds | P
TC1586: Verify a screen reader allows user to hear audio of primary navigation bar | US2221 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:08 PM EST | Donald Fowlds | P
TC1587: Verify a screen reader allows user to hear audio of main content area elements | US2221 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:08 PM EST | Donald Fowlds | P
TC1588: Verify a screen reader allows user to hear audio indicating the have navigated to product pages | US2221 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:09 PM EST | Donald Fowlds | P
TC1589: Validate link to eRevenue Resource SharePoint Training Portal - From NPI Home Page (Selects OK) | US1407 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:54 AM EST | Donald Fowlds | P
TC1590: Validate link to eRevenue Resource SharePoint Training Portal - From Non MCCF Home Page (Selects OK) | US1407 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:55 AM EST | Donald Fowlds | P
TC1750: Verify the TAS core portal links are consistent across all eRevenue Resource link product pages | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:05 PM EST | Donald Fowlds | P
TC1755: Verify eRevenue Resource Product Warning status messages are unable to open simultaneously | US1407 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:01 PM EST | Donald Fowlds | P
TC1845: Verify functionality of each Image icon | US3010 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:12 PM EST | Donald Fowlds | P
TC1845: Verify functionality of each Image icon | US3010 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:06 PM EST | Donald Fowlds | P
TC1855: Verify functionality of system keys are not overwritten. | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:23 PM EST | Donald Fowlds | P
TC1855: Verify functionality of system keys are not overwritten. | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:59 AM EST | Donald Fowlds | P
TC1856: Verify screen reader functions with the ""Warning"" pop up | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:25 PM EST | Donald Fowlds | P
TC1856: Verify screen reader functions with the ""Warning"" pop up | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:04 PM EST | Donald Fowlds | P
TC1857: Verify user cannot access any element outside of the 'Warning' Pop up box when the 'Warning' pop-up is displayed with the use of a keyboard only | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:38 PM EST | Donald Fowlds | P
TC1857: Verify user cannot access any element outside of the 'Warning' Pop up box when the 'Warning' pop-up is displayed with the use of a keyboard only | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:02 PM EST | Donald Fowlds | P
TC1902: Verify keyboard access with non-scripted elements | US3007 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:13 PM EST | Donald Fowlds | P
TC1902: Verify keyboard access with non-scripted elements | US3007 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:00 PM EST | Donald Fowlds | P
TC1907: Verify MCCF EDI TAS Portal loading page can be read by a screen reader | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:40 PM EST | Donald Fowlds | P
TC1907: Verify MCCF EDI TAS Portal loading page can be read by a screen reader | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:05 PM EST | Donald Fowlds | P
TC1921: Verify user cannot access any element outside of the 'Warning' Pop up box when the 'Warning' pop-up is displayed with the use of a keyboard and mouse | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:44 PM EST | Donald Fowlds | P
TC1921: Verify user cannot access any element outside of the 'Warning' Pop up box when the 'Warning' pop-up is displayed with the use of a keyboard and mouse | US3008 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:03 PM EST | Donald Fowlds | P
TC1929: Verify structured lists in containers can be read by a screen reader | US2202 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:45 PM EST | Donald Fowlds | P
TC1930: Verify headings are tagged as headings | US2202 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:26 PM EST | Donald Fowlds | P
TC2071: Verify the eBusiness Solutions footer link has sufficient color contrast | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:38 PM EST | Donald Fowlds | P
TC2111: Verify the Provide Feedback link has sufficient color contrast | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:40 PM EST | Donald Fowlds | P
TC2113: Verify the Return to Top link on the Homepage has sufficient color contrast | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:34 PM EST | Donald Fowlds | P
TC2127: Verify the eBusiness Solutions footer link has an accessible name | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:23 PM EST | Donald Fowlds | P
TC2142: Verify the email link has an accessible name | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:38 PM EST | Donald Fowlds | P
TC2143: Footer VA Logo has alternative text, role=""presentation"" or role=""none"" | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:17 PM EST | Donald Fowlds | P
TC2218: Verify After 20 Seconds the New Redirect Message Does Not Remain Open | US2106 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:44 PM EST | Donald Fowlds | P
TC2250: Verify the breadcrumb on the ePharmacy page has appropriate attributes describing the state or properties. | US3212 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:22 PM EST | Donald Fowlds | P
TC2306: Verify Accordion Title Bar uses only allowed ARIA Attributes | US3547 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:15 PM EST | Donald Fowlds | P
TC2307: Verify Accordion Title Bar uses only allowed ARIA Attribute Values | US3547 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:35 PM EST | Donald Fowlds | P
TC2308: Verify Accordion Title Bar uses indicates the expanded and collapsed state using aria-selected | US3547 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:44 PM EST | Donald Fowlds | P
TC2776: Verify the SSOi provides the Centralized Login Page authentication - US3816 | US3816 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:59 AM EST | Donald Fowlds | P
TC2778: Verify SSOi presents an error message for failure to authenticate to SSOi with the use of a PIV option - US3816 | US3816 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:00 PM EST | Donald Fowlds | P
TC2784: Verify the SSOi functionality of the 60 minute idle timeout option - US3816 | US3816 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:59 AM EST | Donald Fowlds | P
TC2786: Verify User logs out of application - US3816 | US3816 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:03 PM EST | Donald Fowlds | P
TC2788: Verify User logs out of application to verifies no external logout or redirect to SSOi - US3816 | US3816 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:58 AM EST | Donald Fowlds | P
TC2794: Compatibility Test | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 02:04 PM EST | Donald Fowlds | P
TC2794: Compatibility Test | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 01:03 PM EST | Donald Fowlds | P
TC2817: Verify correct functionality of the Skip to Main Content button with assistive technology programs | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:19 PM EST | Donald Fowlds | P
TC2818: Verify correct functionality of the eRevenue Resources Link with assistive technology programs | US3212 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:36 PM EST | Donald Fowlds | P
TC2819: Verify items that Visually appear as navigation links are listed as links and are not associated with a bullet list of content | US3212 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:41 PM EST | Donald Fowlds | P
TC2820: Verify the Return to Top link is tagged as a link | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:40 PM EST | Donald Fowlds | P
TC2823: Verify correct functionality of the 'Here's How You Know' with assistive technology programs | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:26 PM EST | Donald Fowlds | P
TC3292: Time Restrictions | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:27 PM EST | Donald Fowlds | P
TC3293: Interactive Content | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:30 PM EST | Donald Fowlds | P
TC3294: 1.4.4 Resize text: Except for captions and images of text, text can be resized without assistive technology up to 200 percent without loss of content or functionality. (Level AA) | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:43 PM EST | Donald Fowlds | P
TC3306: Verify search input boxes contrast ratio | US3584 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:17 PM EST | Donald Fowlds | P
TC3307: Verify search input boxes have correct labels | US3584 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:39 PM EST | Donald Fowlds | P
TC3309: Verify search buttons can be activated by keyboard | US3584 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:13 PM EST | Donald Fowlds | P
TC3366: WCAG 3.3.2 | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:29 PM EST | Donald Fowlds | P
TC3367: WCAG 1.3.1 | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:24 PM EST | Donald Fowlds | P
TC3368: WCAG 4.1.2 | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:22 PM EST | Donald Fowlds | P
TC3398: WCAG 2.4.5 Multiple Ways | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:17 PM EST | Donald Fowlds | P
TC3399: WCAG 1.4.3 Contrast | US3581 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:13 PM EST | Donald Fowlds | P
TC3451: Verify Logout link displays on the eBusiness Solutions Portal Pages - US3816 | US3816 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 11:58 AM EST | Donald Fowlds | P
TC3512: Verify User logs out of application - US3816 | US3816 | S2 | TAS.01.00.1545_20181219_103623 | 12/19/2018 12:05 PM EST | Donald Fowlds | P