## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TAS v2.0 Requirements Traceability Matrix Build 10 includes 4 components:
1. Web UI — TAS.02.00.4_20190502_140102 2. TAS API — TAS_API.01.00.65_20190422_212745 3. FHIR — VA-FHIR-Server_02.00.5_20190507_141937 4. VistALink — VAVLGateway_02.00.3_20190516_084015
May 17, 2019
Version 6.0

## Revision History
Revision History
Date | Version | Description | Author
05-17-2019 | 6.0 | Updated new version #s post SwA | Donald Fowlds
05-14-2019 | 5.0 | Updated version numbers for services | Donald Fowlds
2019-05-08 | 4 | Added tabs for individual services | Donald Fowlds
2019-05-07 | 3.0 | Added version numbers for services | Donald Fowlds
2019-04-29 | 2.0 | Added US5027 | Donald Fowlds
2019-04-26 | 1 | Final | Donald Fowlds

## Web UI Traceability
User Story ID | User Story Summary | Testable | Acceptance Criteria (for Not Testable US) | Release to be Implemented | Sprint | Test Case ID (for Testable US) | Pass/Fail/Not Tested | Build Last Tested | Comments Failed US- Defect ID Not Testable Comment
US5027 | Change Order of Product Lines in the Navigation Bar of TAS Portal | Y | NA | B10 | S2 | TC3621 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4670 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4671 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4672 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4673 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4674 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4675 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4676 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4677 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4678 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4679 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4680 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4681 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4682 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4683 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4684 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4685 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4686 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4687 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4688 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4689 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4690 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4692 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4693 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4696 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4697 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4903 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4904 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4910 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4913 | Pass | TAS.02.00.4_20190502_140102
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4919 | Pass | TAS.02.00.4_20190502_140102 | DE1334

## TAS API Traceability
User Story ID | User Story Summary | Testable | Acceptance Criteria (for Not Testable US) | Release to be Implemented | Sprint | Test Case ID (for Testable US) | Pass/Fail/Not Tested | Build Last Tested | Comments Failed US- Defect ID Not Testable Comment
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4688 | Pass | TAS_API.01.00.65_20190422_212745

## FHIR Traceability
User Story ID | User Story Summary | Testable | Acceptance Criteria (for Not Testable US) | Release to be Implemented | Sprint | Test Case ID (for Testable US) | Pass/Fail/Not Tested | Build Last Tested | Comments Failed US- Defect ID Not Testable Comment
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4688 | Pass | VA-FHIR-Server_02.00.5_20190507_141937

## VistALink Traceability
User Story ID | User Story Summary | Testable | Acceptance Criteria (for Not Testable US) | Release to be Implemented | Sprint | Test Case ID (for Testable US) | Pass/Fail/Not Tested | Build Last Tested | Comments Failed US- Defect ID Not Testable Comment
US7005 | Screen UI - TAS Application Monitoring Services (T) B10S4 | Y | NA | B10 | S2 | TC4688 | Pass | VAVLGateway_02.00.3_20190516_084015