## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TASCore TAS.01.00.1517_20181108_103103
2018-11-14
Version 1.0

## Revision History
Revision History
Date | Version | Description | Author
11/14/18 | 1 | Initial | Lisa Bruno/Donald Fowlds

## RTM
User Story ID | User Story Summary | Testable | Acceptance Criteria (for Not Testable US) | Release to be Implemented | Sprint | Test Case ID (for Testable US) | Pass/Fail/Not Tested | Build Last Tested | Comments Failed US- Defect ID Not Testable Comment
US5027 | Change Order of Product Lines in the Navigation Bar of TAS Portal | Y | NA | B6 | SS | TC3621 | Pass | TAS.01.00.1517_20181108_103103
US5027 | Change Order of Product Lines in the Navigation Bar of TAS Portal | Y | NA | B6 | SS | TC3626 | Pass | TAS.01.00.1517_20181108_103103
US5027 | Change Order of Product Lines in the Navigation Bar of TAS Portal | Y | NA | B6 | SS | TC3732 | Pass | TAS.01.00.1517_20181108_103103