## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TASCore TAS.01.00.49_20170928_073548 Defect Log
October 3, 2017
Version 1.0

## Revision History
Revision History
Date | Version | Description | Author
2017-10-03 | 1 | Draft | Lisa Bruno

## Defect Log
Defect ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE323 | NA | Ill-Designed Page Navigation Warning (IE) | 3 - Medium | Closed | 2017-09-22 | No User Story - Duplicate Defect | TC1753 - Verify the eProduct eRevenue Resource link warning messages do not open be at the Top of screen (duplicate) | 2017-09-28
DE324 | NA | eBusiness Calendar Columns | 3 - Medium | Closed | 2017-09-22 | No User Story - Backlog Repair | TC NA - Future Build No test case at this time | 2017-09-27
DE326 | NA | eProduct eRevenue Resource link warning message should not be at the Top of screen | 3 - Medium | Closed | 2017-09-25 | US1406: Define Layout of the MCCF EDI Home Page | TC1753 - Verify the eProduct eRevenue Resource link warning messages do not open be at the Top of screen | 2017-09-28
DE327 | NA | 'Warning Status' should display as 'Warning' on eRevenue Resource pop up message | 4 - Low | Closed | 2017-09-25 | US1406: Define Layout of the MCCF EDI Home Page | TC1754 - Verify the 'Warning Status' should display as 'Warning' on eRevenue Resource pop up message | 2017-09-28
DE328 | NA | Site Wide Search remains open and should not overlap | 3 - Medium | Closed | 2017-09-25 | US1406: Define Layout of the MCCF EDI Home Page | TC1564 - Selecting the "Site-wide Search" drop-down button in expands an accordion with an additional search form for user input and does not remain open | 2017-09-28
DE329 | NA | Should not be able to open Two pop up Warning status messages simultaneously | 3 - Medium | Closed | 2017-09-25 | US1407: Add link to eRevenue Resource SharePoint Training Portal | TC1755 - Verify eRevenue Resource Product Warning status messages are Unable to | 2017-09-28
DE330 | NA | Countdown timer is at 10 seconds vs. 20 seconds when selecting to navigate away from TAS | 2 - High | Closed | 2017-09-25 | US2220: (Copy of) 508.01.02.16 Web Application Timed Response (1194.22P) | TC1187 - Verify a timer is available to user when about to navigate away from site | 2017-09-27
DE331 | NA | ICB Web link -is not navigating off eInsurance home page | 3 - Medium | Closed | 2017-09-26 | US1408: Add link to Insurance Capture Buffer (ICB) Web | TC1773 - Verify the (ICB) Web link | 2017-09-28