## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TASCore TAS.01.00.203_20180607_163807 Defect Log
June 18, 2018
Version 2.0

## Revision History
Revision History
Date | Version | Description | Author
March 9, 2018 | 1 | Draft | Lisa Bruno/ Donald Fowlds
June 18, 2018 | 2 | Draft | Lisa Bruno/ Donald Fowlds

## Defect Log
ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE458 | NA | Current Days Date on Calendar is Not Showing Highlighted | 4 - Low | Closed | 01/05/2018 05:19 PM EST | US3213: Remove All Product Specific Content Boxes from the MCCF EDI TAS Portal Home Page | TC2165 | 01/10/2018 09:16 AM EST
DE482 | NA | eRevenue Resource should be eRevenue Resources | 4 - Low | Closed | 01/24/2018 01:16 PM EST | US3212: Enhance Linking to URLs from the MCCF EDI TAS Portal | TC2172 | 03/07/2018 02:00 PM EST
DE485 | NA | Breadcrumb Not Being Displayed on FAQ, Help or Contact Us Pages | 4 - Low | Closed | 01/25/2018 09:20 PM EST | US3212: Enhance Linking to URLs from the MCCF EDI TAS Portal | TC2177 | 02/16/2018 11:45 AM EST
DE510 | NA | Inconsistent Page Display - eInsurance | 4 - Low | Closed | 02/14/2018 09:54 AM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2516 | 03/02/2018 09:00 AM EST
DE511 | NA | Color #0071bc used in BreadCrumbs section are not listed in Color Palette | 4 - Low | Closed | 02/14/2018 12:11 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2366 | 02/22/2018 11:06 AM EST
DE512 | NA | Colors in the Alerts section of the style guide for used for Tertiary (content driven messages and alerts sections) do not have matching colors in the color palette of the style guide. | 4 - Low | Closed | 02/14/2018 12:41 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2354 | 02/22/2018 11:11 AM EST
DE513 | NA | Calendar buttons do not reflect an active state when selected. | 4 - Low | Closed | 02/14/2018 12:59 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2409 | 03/02/2018 08:49 AM EST
DE514 | NA | Header Background-Position is set to 0 when style guide states it should be 'Left' | 4 - Low | Closed | 02/14/2018 02:02 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2352 | 02/23/2018 10:14 AM EST
DE517 | NA | Style Guide: All Heading 6 elements - Line Height is Incorrect - should be 1.3 not 1.5 | 3 - Medium | Closed | 02/15/2018 12:07 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2346 | 02/22/2018 11:19 AM EST
DE518 | NA | All breadcrumbs font size and line-height do not match style guide | 4 - Low | Closed | 02/15/2018 12:53 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2362 | 02/22/2018 11:23 AM EST
DE521 | NA | Visited Hyperlink Text does NOT Remain Purple After it has been Selected | 3 - Medium | Closed | 02/16/2018 01:21 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2360 | 03/01/2018 12:40 PM EST
DE522 | NA | Secondary background color #003e73 not in color palette | 4 - Low | Closed | 02/16/2018 03:10 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2327 | 02/22/2018 11:29 AM EST
DE552 | NA | Cannot tab-focus Return to top link | 2 - High | Closed | 03/02/2018 09:00 AM EST | US1406: Define Layout of the MCCF EDI Home Page | TC1492 | 03/06/2018 08:54 AM EST
DE553 | NA | Cannot tab focus X in search box (IE only) | 2 - High | Closed | 03/02/2018 10:23 AM EST | US2216: (Copy of) 508.01.02.12 Web Application Scripting (1194.22L-2) | TC1180 | 03/07/2018 09:11 AM EST
DE554 | NA | 'Skip to main content' link does not skip tab focus of navigation links | 2 - High | Closed | 03/02/2018 10:48 AM EST | US2219: (Copy of) 508.01.02.15 Web Application Skip Navigation (1194.22O) | TC1186 | 03/05/2018 09:01 AM EST
DE555 | NA | 'Skip to main content' link removes breadcrumb location | 4 - Low | Closed | 03/02/2018 10:52 AM EST | US2219: (Copy of) 508.01.02.15 Web Application Skip Navigation (1194.22O) | TC1186 | 03/05/2018 08:59 AM EST
DE643 | NA | 508 Audit Findings - Content is not tagged properly for assistive technology users | 1 - Critical | Closed | 04/16/2018 10:34 AM EST | US3581: Review New v2.0 508 compliance user stories | TC2817 | 05/15/2018 02:52 PM EST
DE644 | NA | 508 Audit Findings - Links are not tagged properly for assistive technology users (IE Browser) | 1 - Critical | Closed | 05/07/2018 03:45 PM EST | US3581: Review New v2.0 508 compliance user stories | TC2818 | 05/15/2018 02:49 PM EST
DE645 | NA | 508 Audit Findings - 4 Links (FAQ,Contact Us, Help and eRevenue Resources) are not tagged properly for assistive technology users. | 1 - Critical | Closed | 04/16/2018 10:38 AM EST | US3581: Review New v2.0 508 compliance user stories | TC2819 | 05/15/2018 02:54 PM EST
DE646 | NA | 508 Audit Findings: Links appear as navigation links and should not be tagged as a list | 1 - Critical | Closed | 04/23/2018 01:31 PM EST | US3581: Review New v2.0 508 compliance user stories | TC2819 | 05/15/2018 02:56 PM EST
DE647 | NA | 508 Audit Findings - The business solutions link at the bottom of the page to return to the home page is tagged as a list of one item | 1 - Critical | Closed | 04/16/2018 10:46 AM EST | US3581: Review New v2.0 508 compliance user stories | TC2819 | 05/15/2018 02:59 PM EST
DE648 | NA | 508 Audit Findings - Return to Top link is not tagged as a link for assistive technology users | 1 - Critical | Closed | 04/16/2018 10:52 AM EST | US3581: Review New v2.0 508 compliance user stories | TC2820 | 05/15/2018 03:00 PM EST
DE649 | NA | 508 Audit Findings: Focus placement with assistive technology does not place the user at the top of the page | 1 - Critical | Closed | 04/16/2018 10:55 AM EST | US3581: Review New v2.0 508 compliance user stories | TC2822 | 05/15/2018 03:01 PM EST
DE650 | NA | 508 Audit Findings: Invisible text is read with assistive technology when content is collapsed | 1 - Critical | Closed | 05/08/2018 12:15 PM EST | US3581: Review New v2.0 508 compliance user stories | TC2823 | 05/15/2018 03:02 PM EST
DE651 | NA | 508 Audit Findings: The name, role and value of elements within the web application are not read by assistive technology programs | 1 - Critical | Closed | 05/02/2018 10:05 AM EST | US3581: Review New v2.0 508 compliance user stories | TC2824 | 05/15/2018 02:47 PM EST
DE652 | NA | 508 Audit Findings - The state of the Expand and Collapsed function for the Here’s How You Know button is not read by assistive technology programs | 1 - Critical | Closed | 04/16/2018 11:08 AM EST | US3581: Review New v2.0 508 compliance user stories | TC2823 | 05/15/2018 03:03 PM EST
DE733 | NA | 508 Audit Findings - Content is not tagged properly for assistive technology users | 1 - Critical | Closed | 05/15/2018 02:55 PM EST | US3581: Review New v2.0 508 compliance user stories | TC2817 | 06/01/2018 09:41 AM EST
DE720 | NA | 508 Audit - When the view port is set to a smaller size the tabbing order is illogical (508 Audit) | 1 - Critical | Closed | 06/05/2018 05:23 PM EST | US1406: Define Layout of the MCCF EDI Home Page | TC1492 | 06/14/2018 11:11 AM EST
DE723 | NA | 508 Audit - Alternative text descriptions are insufficient for assistive technology users (508 Audit) VA Logo Footer | 1 - Critical | Closed | 05/15/2018 03:35 PM EST | US3581: Review New v2.0 508 compliance user stories | TC1561 | 06/01/2018 09:42 AM EST
DE725 | NA | 508 Audit - On the home page, above the search box the words Search Small are read with assistive technology programs (508 Audit) | 1 - Critical | Closed | 05/18/2018 10:24 AM EST | US3581: Review New v2.0 508 compliance user stories | TC3368 | 06/01/2018 09:42 AM EST
DE729 | NA | 508 Audit - On all pages of the application a bread crumb is used -A greater than sign is used to make a visual correlation of the path a user took to get to a specific page | 1 - Critical | Closed | 05/15/2018 04:00 PM EST | US3581: Review New v2.0 508 compliance user stories | TC3367 | 06/01/2018 09:43 AM EST
DE732 | NA | 508 Audit - Links are not correctly read by assistive technology programs- link should read as it appears visually on the page | 1 - Critical | Closed | 05/15/2018 03:55 PM EST | US3581: Review New v2.0 508 compliance user stories | TC1561 | 05/17/2018 02:54 PM EST
DE766 | NA | UAT 508 Audit - When the main 'Menu' function is not read by assistive technology programs | 1 - Critical | Closed | 06/01/2018 04:25 PM EST | US3581: Review New v2.0 508 compliance user stories | TC3368 | 06/14/2018 11:12 AM EST