## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TASCore TAS.01.00.203_20180607_163807 Defect Log
July 17, 2018
Version 3.0

## Revision History
Revision History
Date | Version | Description | Author
March 9, 2018 | 1 | Draft | Lisa Bruno/ Donald Fowlds
June 18, 2018 | 2 | Draft | Lisa Bruno/ Donald Fowlds
July 17, 2018 | 3 | Final | Lisa Bruno/Donald Fowlds

## Defect Log
ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE458 | NA | Current Days Date on Calendar is Not Showing Highlighted | 4 - Low | Closed | 01/05/2018 05:19 PM EST | US3213: Remove All Product Specific Content Boxes from the MCCF EDI TAS Portal Home Page | TC2165 | 01/10/2018 09:16 AM EST
DE482 | NA | eRevenue Resource should be eRevenue Resources | 4 - Low | Closed | 01/24/2018 01:16 PM EST | US3212: Enhance Linking to URLs from the MCCF EDI TAS Portal | TC2172 | 03/07/2018 02:00 PM EST
DE485 | NA | Breadcrumb Not Being Displayed on FAQ, Help or Contact Us Pages | 4 - Low | Closed | 01/25/2018 09:20 PM EST | US3212: Enhance Linking to URLs from the MCCF EDI TAS Portal | TC2177 (also occurs in TC2287, TC2286) | 02/16/2018 11:45 AM EST
DE510 | NA | Inconsistent Page Display - eInsurance | 4 - Low | Closed | 02/14/2018 09:54 AM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2516 | 03/02/2018 09:00 AM EST
DE511 | NA | Color #0071bc used in BreadCrumbs section are not listed in Color Palette | 4 - Low | Closed | 02/14/2018 12:11 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2366 | 02/22/2018 11:06 AM EST
DE512 | NA | Colors in the Alerts section of the style guide for used for Tertiary (content driven messages and alerts sections) do not have matching colors in the color palette of the style guide. | 4 - Low | Closed | 02/14/2018 12:41 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2354 | 02/22/2018 11:11 AM EST
DE513 | NA | Calendar buttons do not reflect an active state when selected. | 4 - Low | Closed | 02/14/2018 12:59 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2409 | 03/02/2018 08:49 AM EST
DE514 | NA | Header Background-Position is set to 0 when style guide states it should be 'Left' | 4 - Low | Closed | 02/14/2018 02:02 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2352 | 02/23/2018 10:14 AM EST
DE517 | NA | Style Guide: All Heading 6 elements - Line Height is Incorrect - should be 1.3 not 1.5 | 3 - Medium | Closed | 02/15/2018 12:07 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2346 | 02/22/2018 11:19 AM EST
DE518 | NA | All breadcrumbs font size and line-height do not match style guide | 4 - Low | Closed | 02/15/2018 12:53 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2362 (also occurs in TC2540) | 02/22/2018 11:23 AM EST
DE521 | NA | Visited Hyperlink Text does NOT Remain Purple After it has been Selected | 3 - Medium | Closed | 02/16/2018 01:21 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2360 | 03/01/2018 12:40 PM EST
DE522 | NA | Secondary background color #003e73 not in color palette | 4 - Low | Closed | 02/16/2018 03:10 PM EST | US3548: Implement TAS Design Standards based on TAS Design Guide and Playbook -Sprint 3 | TC2327 | 02/22/2018 11:29 AM EST