## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TAS v2.0 Defect Log Build 10 includes 4 components:
1. Web UI — TAS.02.00.4_20190502_140102 2. TAS API — TAS_API.01.00.65_20190422_212745 3. FHIR — VA-FHIR-Server_02.00.5_20190507_141937 4. VistALink — VAVLGateway_02.00.3_20190516_084015
May 17, 2019
Version 4.0

## Revision History
Revision History
Date | Version | Description | Author
05-17-2019 | 4.0 | Updated new version #s post SwA | Donald Fowlds
05-14-2019 | 3.0 | Updated services version numbers | Donald Fowlds
2019-05-08 | 2 | Added tabs for individual services | Donald Fowlds
2019-04-26 | 1 | Draft | Donald Fowlds

## Web UI Defects
ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
1334 | NA | Dashboard report information links do not conform to WCAG 2.4.4 Link Purpose (In Context): | High | Closed | 2019-04-19 | US7005 | TC4919 | 2019-04-26

## TAS API Defects
ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
None

## FHIR Defects
ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
None

## VistALink Defects
ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
None