## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TASCore TAS.01.00.121_20171213_164037 Defect Log
December 18, 2017
Version 1.0

## Revision History
Revision History
Date | Version | Description | Author
December 18, 2017 | 1 | Draft | Lisa Bruno

## Defect Log
ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
DE352 | NA | 'Warning' pop up message does not have sole focus via the use of a keyboard. | 2 - High | Closed | 10/20/2017 01:38 PM EDT | US3008: (Copy of) 508.01.01.02 Software Application Accessibility Features API (1194.21) | TC1857 | 11/21/2017 10:07 AM EST
DE370 | NA | No interpretive elements on screen for screen reader on Page Loading screen | 2 - High | Closed | 11/02/2017 03:16 PM EDT | US3008: (Copy of) 508.01.01.02 Software Application Accessibility Features API (1194.21) | TC1907 | 12/14/2017 12:24 PM EST
DE404 | NA | Skip to main content is not visible (508 Audit Findings) | 1 - Critical | Closed | 11/22/2017 03:15 PM EST | US2219: (Copy of) 508.01.02.15 Web Application Skip Navigation (1194.22O) | TC1186 | 12/18/2017 12:31 PM EST
DE405 | NA | Column headers are not associated with respective columns (508 Audit Findings) | 1 - Critical | Closed | 11/22/2017 03:30 PM EST | US2211: (Copy of) 508.01.02.07 Web Application Table Headers (1194.22G) | TC1521 | 12/18/2017 12:48 PM EST
DE406 | NA | Lists are not structured properly (508 Audit Findings) | 1 - Critical | Closed | 11/22/2017 03:46 PM EST | US2202: (Copy of) 508.01.07 Functional Performance Criteria (1194.31) | TC1929 | 12/18/2017 12:51 PM EST
DE407 | NA | Headings structure is incorrectly ordered (508 Audit Findings) | 1 - Critical | Closed | 11/24/2017 09:45 AM EST | US2202: (Copy of) 508.01.07 Functional Performance Criteria (1194.31) | TC1930 | 12/18/2017 01:10 PM EST
DE408 | NA | Each page does not have a unique title (508 Audit Findings) | 1 - Critical | Closed | 11/24/2017 10:03 AM EST | US2202: (Copy of) 508.01.07 Functional Performance Criteria (1194.31) | TC1931 | 12/18/2017 01:13 PM EST