## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TASCore TAS.01.00.1453_20180824_134457
August 28, 2018
Version 2.0

## Revision History
Revision History
Date | Version | Description | Author
08/28/2018 | 1 | Initial | Lisa Bruno/Donald Fowlds
11/29/2018 | 2 | Revised | Lisa Bruno/Donald Fowlds

## Defect Log
ID | Summary | Description | Severity | Status | Created Date | Affected User Story (If known) | Test Case | Resolution Date | Workaround (Only for Defects being deployed to Prod, even if None is specified)
1052 | NA | B5 508 Audit - Focus placement with assistive technology does not place the user at the top of the page | Critical | Closed | 2018-11-29 | US3581 | Ad Hoc 508 Testing | Backlog repair | Release will not be available to end-users. Repair to be made in next build.
1053 | NA | B5 508 Audit - On the contact Us page under Contact Info the links for the email address and provide feedback are read as a menu. | Critical | Closed | 2018-11-29 | US3581 | Ad Hoc 508 Testing | Backlog repair | Release will not be available to end-users. Repair to be made in next build.
1054 | NA | B5 508 Audit - the menu Button is read as Menu Button collapsed when the menu is expanded and when the menu is collapsed. | Critical | Closed | 2018-11-29 | US3581 | Ad Hoc 508 Testing | Backlog repair | Release will not be available to end-users. Repair to be made in next build.