## Cover
Department of Veterans Affairs
Medical Care Collection Fund (MCCF) Electronic Data Interchange (EDI) Transaction Applications Suite (TAS) TASCore TAS.01.00.1517_20181108_103103
November 14, 2018
Version 1.0

## Revision History
Revision History
Date | Version | Description | Author
11/14/2018 | 1 | Initial | Donald Fowlds/ Lisa Bruno

## Test Execution Log
Test Case ID | User Story | Sprint | Build Executed | Date Executed | Tested By | Test Results (P/F) | Defect ID (Failed Tests)
TC3621: Verify order of the eProducts are now displayed in alphabetical order | US5027 | B6 S3 | TAS.01.00.1490_20181009_144754 | 10/10/2018 07:24 AM EDT | Lisa Bruno | P
TC3621: Verify order of the eProducts are now displayed in alphabetical order | US5027 | B6 SS | TAS.01.00.1517_20181108_103103 | 11/08/2018 10:33 AM EST | Lisa Bruno | P
TC3626: Verify order of the eProducts are now displayed in alphabetical order | US5027 | B6 S3 | TAS.01.00.1490_20181009_144754 | 10/10/2018 07:24 AM EDT | Lisa Bruno | P
TC3626: Verify order of the eProducts are now displayed in alphabetical order | US5027 | B6 SS | TAS.01.00.1517_20181108_103103 | 11/08/2018 10:33 AM EDT | Lisa Bruno | P
TC3732: Verify the Change Order of Product Lines in the Navigation Bar of TAS Portal | US5027 | B6 S3 | TAS.01.00.1490_20181009_144754 | 10/19/2018 10:17 AM EDT | Kimberly Battles | P
TC3732: Verify the Change Order of Product Lines in the Navigation Bar of TAS Portal | US5027 | B6 SS | TAS.01.00.1517_20181108_103103 | 11/08/2018 10:59 AM EDT | Kimberly Battles | P